MOPANI DISTRICT MUNICIPALITY

IMPLEMENTATION PLAN

KPA 1:  Municipal Transformation and Organisational Development

| NO | PLANNED INTERVENTIONS | HIGH LEVEL ACTIVITIES | DELIVERABLES | TIMEFRAMES | RESPONSIBILITY |
| --- | --- | --- | --- | --- | --- |
| 1. | Organisational Design and Human Resource Capacity |  |  |  |  |
| 1.2 | Filling of all vacant section 57 managers posts | Conduct an audit of all vacant senior management positions within the district. | Vacant positions filled in all municipalities. | June 2007 | Municipal Managers, Corporate Service Managers |
| 1.3 | Signing of employment contracts by all Section 57 managers for the 2007/08 fy | Facilitate the signing of employment where it has not been signed. | Signed employment contracts for all Section 57 employees. | June 2007 | Municipal Managers, Corporate Service Managers |
| 1.4 | Review of the organogram of the municipality to ensure alignment with the IDP/ Budget | Conduct an assessment on the capacity of the municipalities to deliver on the IDP with the available and envisaged resources. | Organogram aligned with the IDP/Budget/PMS | June 2007 | Municipal Managers, Corporate Service Managers, CFO, Planning and Economic Development Managers |
| 1.5 | Completion of the placement of staff in terms of Section 78 of the Municipal Systems Act (2000) | Conduct an assessment on the completion of the Section 78 process in terms of Water and Environmental Health Services. | The transferred staff placed on the organogram of municipalities. | September 2007 | Municipal Managers, Corporate Service Managers |
| 2. | Employment Equity |  |  |  |  |
| 2.1 | Employment Equity Plan | Conduct an evaluation of the existing plans in terms of progress made. | Reviewed Employment Equity targets. | June 2007 | Municipal Managers, Corporate Service Managers |
| 2.2 | Women representation in Section 57 Managers | Conduct an audit of women occupying senior management positions in all municipalities. | Employment of women in Section 57 positions. | June 2007 | Municipal Managers, Corporate Service Managers |
| 2.3 | Total number of woman employed by the municipality against total staff | Conduct an audit of gender balance in all municipalities. | Gender balance in all municipalities. | June 2008 | Municipal Managers, Corporate Service Managers |
| 2.4 | Total number of disable staff in management level | Conduct an audit on the representation of disabled people in management levels of municipalities. | People with disabilities appointed in management levels of municipalities. | June 2008 | Municipal Managers, Corporate Service Managers |
| 3. | Skills Development |  |  |  |  |
| 3.1 | Work Place Skills Development Plan submitted to LGSETA | Conduct an assessment of the Workplace Skills Development Plans submitted to LGSETA by municipalities. | Workplace Skills Development Plans approved by Councils. | August 2007 | Municipal Managers, Corporate Service Managers, Skills Development Facilitators |
| 3.2 | Section 57 Managers development program | Develop a programme to capacitate Section 57 Managers. | Targeted and focused programme developed for Section 57 Managers. | August 2007 | Municipal Managers, Corporate Service Managers |
| 3.3 | Skill Levy Rebate | Conduct an assessment of the Skills levy rebate received by municipalities. | Report on the Skills levy rebate for all municipalities. | August 2007 | Municipal Managers, Corporate Service Managers |
| 4. | Integrated Development Planning |  |  |  |  |
| 4.1 | Appointment of IDP officers | Identify vacant positions for IDP Officers in municipalities. | IDP Officers appointed in all municipalities | July 2007 | Municipal Managers, Corporate Service Managers |
| 4.2 | 2007/08- 2012/13 IDP | Develop the five year IDP for municipalities. | Five year IDP’s approved by Council. | May 2007 | Municipal Managers, Planning and Economic Development Managers |
| 4.3 | Core sector plan included in the IDP (Spatial Development Framework , Disaster Management, MTIEF; Environmental Management Plans etc) | Identify the plans that are not included in the IDP. | Sector Plans developed and approved by Council. | May 2008 | Municipal Managers, Planning and Economic Development Managers |
| 5. | Functionality of the Performance Management System in compliance with Chapter of 6 of the MSA |  |  |  |  |
| 5.1 | Approved PMS policy and implementation framework in place | Conduct an assessment and review of the PMS policy and framework. | Reviewed PMS policy and Framework. | May 2007 | Municipal Managers, Planning and Economic Development Managers |
| 5.2 | Conducting of institutional performance review on periodic basis | Conduct an evaluation of the institutional performance review. | Quarterly and annual performance report | On-going | Municipal Managers, Planning and Economic Development Managers |
| 5.4 | Compliance with the Performance Regulation on Section 57 managers | Conduct an audit on the performance agreement and plans of the Section 57 Managers in line with the Performance Regulation. | Performance contracts and plans aligned to the new regulations. | June 2007 | Municipal Managers, Corporate Service Managers |

KPA 2: Basic Service Delivery

| NO | PLANNED INTERVENTIONS | HIGH LEVEL ACTIVITIES | DELIVERABLES | TIMEFRAME | RESPONSIBILITY |
| --- | --- | --- | --- | --- | --- |
| 1. | Water Services |  |  |  |  |
| 1.1 | Free Basic Water Services | - Complete and update the indigent registers; - Implement the Indigent Policy | Indigent people provided with free basic water services. | June 2008 | Municipal Managers, Technical Managers |
| 1.2 | All communities have access to clean water and decent sanitation by 2010 | - Verify and update the backlogs; - Evaluate progress made with regard to the implementation plan. | Funding proposal developed and implemented. | March 2008 | Municipal Managers, Technical Managers |
| 1.3 | Verification of municipal backlog | - Verify and update the backlogs; - Evaluate progress made with regard to the implementation plan. | Funding proposal developed and implemented. | May 2007 | Municipal Managers, Technical Managers |
| 1.4 | Water and sanitation at all schools | - Conduct an assessment on the state of water and sanitation at schools, - Incorporate all schools in the implementation plan | - Funding proposal developed and implemented. | June 2008 | Municipal Managers, Technical Managers |
| 1.5 | Water and sanitation at all clinics | - Conduct an assessment on the state of water and sanitation at clinics, - Incorporate all clinics in the implementation plan | - Funding proposal developed and implemented. | June 2008 | Municipal Managers, Technical Managers |
| 1.6 | Reduction of unaccounted for water | - Conduct a technical assessment of all the water schemes and facilities, - Develop a refurbishment plan, - Develop a maintenance plan for all water facilities. | - Funding proposal developed; - District Maintenance Plan developed and approved by Council and a; - Refurbishment plan developed and approved by Council | June 2007 | Municipal Managers, Technical Managers |
| 2. | Electricity |  |  |  |  |
| 2.1 | Access to Free Basic Electricity | - Complete and update the indigent registers; - Implement the Indigent Policy | Indigent people provided with free basic electricity. | June 2008 | Municipal Managers, Technical Managers and Eskom |
| 2.2 | New electricity connections | - Conduct an assessment of all new connections made within municipalities. | Backlogs identified. | May 2007 | Municipal Managers, Technical Managers and Eskom |
| 2.3 | National Target : Electricity for all by 2012 | - Complete and update electricity backlogs; - Provide costing for all the backlogs; - Develop an implementation plan and funding proposal. | Funding proposal and implementation plan developed and approved by Council | May 2007 | Municipal Managers, Technical Managers and Eskom |
| 3. | Waste Removal |  |  |  |  |
| 3.1 | Waste Removal Policy | - Conduct an audit on waste management; - Develop and implement a waste removal policy. | - Waste Removal policy developed and approved by Council. | June 2008 | Municipal Manager, Community/ Public Services Managers |
| 3.2 | Waste Removal Strategy | - Complete and verify waste removal backlogs; | - Waste Removal strategy developed and approved by Council. | June 2008 | Municipal Manager, Community/ Public Services Managers |
| 4. | Roads and storm water |  |  |  |  |
| 4.1 | Roads Infrastructure Strategy | - Conduct an audit on road infrastructure network; - Develop and implement a Roads Infrastructure Strategy. | - Roads Infrastructure Strategy developed and approved by Council. | June 2008 | Municipal Managers, Technical Managers |
| 4.2 | New roads planned | - Complete and verify roads infrastructure backlogs; | - Plan for the new roads network developed, costed and implemented. | June 2008 | Municipal Managers, Technical Managers |
| 4.3 | Maintenance and Rehabilitation of roads and storm water drainage | - Conduct a technical assessment of all the road networks and storm water drainage, - Develop a maintenance plan for all road networks and storm water drainage. | - Rehabilitation plan developed and approved by Council; - Maintenance plan developed and approved by Council. | June 2008 | Municipal Managers, Technical Managers |
| 5. | Indigent Policy Implementation Framework |  |  |  |  |
| 5.1 | Development of indigent policies in municipalities | - Conduct an audit on the implementation of the Indigent Policy | - Reviewed Indigent Policy | May 2007 | Municipal Managers; CFO and Planning and Economic Development Managers. |
| 5.2 | Development of indigent registers | - Complete and update the indigent registers; | - Reviewed and updated Indigent Registers. | May 2007 | Municipal Managers; CFO and Planning and Economic Development Managers. |
| 6. | Municipal Infrastructure Grant |  |  |  |  |
| 6.1 | Development of Municipal Infrastructure Investment Framework Strategy | - Conduct an audit on Infrastructure investment; - Highlight gaps in the approach on infrastructure investment in municipalities. | - Municipal Infrastructure Investment Strategy developed and approved by Council | September 2007 | Municipal Managers; CFO and Planning and Economic Development Managers. |
| 6.2 | Development of Land Use Management Planning system | - Conduct an audit on land use management system; - Highlight gaps in the approach on land use management in municipalities. | - Land Use Management System developed and approved by Council | September 2007 | Municipal Managers, Technical Managers |
| 6.3 | Improving expenditure on MIG | - Conduct an assessment on the spending on MIG; - Identify and record the implementation gaps; - Develop an implementation strategy on MIG | - Expenditure report analysed; - An implementation strategy developed and implemented. | Quarterly | Municipal Managers, Technical Managers |
| 6.4 | Alignment of MIG with EPWP | - Conduct an audit of projects implemented through the EPWP method; | - Projects implemented through the EPWP method. | On-going | Municipal Managers, Technical Managers |
| 7. | Municipal Housing Plan & strategy implementation |  |  |  |  |
| 7.1 | Municipal Housing Plan | - Conduct and update a housing backlogs; | - Municipal Housing Plan developed and approved by Council. |  | Municipal Managers, Community/ Public Service Managers |
| 7.2 | Housing Beneficiary List | - Identify and record beneficiaries for housing provision; - Evaluate and assess qualifying members; - Identify and ensure development of land for housing; - Develop a priority list for implementation. | - Housing beneficiary list developed and approved by Council; - Land for housing delivery identified and developed. |  | Municipal Managers, Community/ Public Service Managers and Technical Managers |

## KPA 3:  Local Economic Development

| NO | PLANNED INTERVENTIONS | HIGH LEVEL ACTIVITIES | DELIVERABLES | TIMEFRAME | RESPONSIBILITY |
| --- | --- | --- | --- | --- | --- |
| 1. | LED STRATEGY |  |  |  |  |
| 1.1 | Alignment of the District LED strategy with Local Municipalities LED Strategies | - Conduct an assessment on the alignment of the District LED strategy to the Local Municipalities LED strategies; - Develop a uniform implementation plan with timeframes. | - An assessment report developed and analysed; - An implementation plan developed and approved by Councils. | September 2007 | Municipal Manager, Planning and Economic Development Managers |
| 1.2 | Alignment of LED Strategy with PGDS, EPWP, ASIGISA; PPP; NSDP; | - Conduct an assessment on the alignment of the LED strategy to the PGDS, EPWP, ASGISA, PPP and NSDP; | - Economic development goals achieved through the available strategies and plans | June 2008 | Municipal Manager, Planning and Economic Development Managers |
| 1.3 | Implementation of District LED Summit Action Plan | - Develop and report on the resolutions of the District Growth and Development Summit | - Progress report presented to Council. | Quarterly | Municipal Manager, Planning and Economic Development Managers |
| 1.4 | Functionality of LED District Forum | - Identify members to serve in the LED Forum; - Develop a framework for the LED Forum and; - Officially launch the LED Forum per local municipality and the District. | - Framework for the LED Forum developed and approved; - LED Forum established in all municipalities. | September 2007 | Municipal Manager, Planning and Economic Development Managers |
| 1.4 | LED units | - Conduct an audit on the existing LED units in municipalities; - Establish fully fledged LED units in municipalities; - Allocate resources for the LED units. | - Effective and efficient LED units established | September 2007 | Municipal Manager, Planning and Economic Development Managers |
| 1.5 | LED job creation initiatives | - Anchor projects identified and funded for all municipalities; - Anchor projects implemented and monitored; - Record number of jobs to be created. | - Job creation initiatives identified and implemented; - Number of jobs to be created confirmed. | June 2008 | Municipal Manager, Planning and Economic Development Managers |

KPA 4:  Municipal Financial Viability and Management: 2006/07

| NO | PLANNED INTERVENTIONS | HIGH LEVEL ACTIVITIES | DELIVERABLES | TIMEFRAME | RESPONSIBILITY |
| --- | --- | --- | --- | --- | --- |
| 1. | MFMA Institutional compliance |  |  |  |  |
| 1.1 | Budget and Treasury Office | - Appointment and recruitment of qualified staff; - Conduct skills audit on the current personnel; - Training and development of the personnel. | - Qualified staff appointed; - Skills audit report; - Capacity building of staff | End of September 2007 | Municipal Manager; CFO |
| 1.2 | MFMA implementation, monitoring and compliance plan | - Implementation, monitoring and compliance plan to be developed; - Progress report submitted to Council | - Implementation, monitoring and compliance report - Reports on implementation | End of June 2007; Monthly | Municipal Manager; CFO |
| 1.3 | Audit Committee | - Establishment of the Audit Committee; - Training of the members of the audit committee on PMS; - Schedule of meetings for Audit Committee developed | - Audit committee established; - Audit committee members provided with relevant information; - Schedule of meetings | End of March 2007; End of May 2007; End of May 2007 | Municipal Manager |
| 1.4 | Internal Audit Unit | - Filling of positions in the Internal Audit; - Establishment of the unit where it does not exist; | - Functional Internal Audit Units | End of June 2007 | Municipal Manager; CFO |
| 2. | Implementation of financial systems, policies, and controls and regulations |  |  |  |  |
| 2.1 | Fraud Prevention and Anti Corruption mechanism and strategies | - Development of the Fraud Prevention and Anti Corruption strategy; - Establishment of the Risk Management Unit | - Fraud prevention and Anti Corruption strategy to be developed; - Risk Management Unit established | End of June 2007; End of June 2008 | Municipal Manager; CFO |
| 2.2 | Delegation of financial powers and functions | - Develop and approve a delegation system of financial powers and functions; - Ensure implementation of the delegation system; | - Delegation system of financial powers and functions developed and approved; - Delegation system implemented. | End of June 2007 | Municipal Manager; CFO |
| 2.3 | Supply Chain Management policy | - Conduct an internal workshop to all staff members in relation to the Supply Chain Management policy; - Ensure establishment and functionality of the Supply Chain Management Committees; - Conduct a continuous audit on the effectiveness of the committees. | - Capacity provided for all staff on the Supply Chain Management policy; - Supply chain management committees established; - Review report on the supply chain management committees developed. | On - going | Municipal Manager; CFO |
| 2.4 | BEE scorecards | - BEE Scorecard developed and approved by Council; - Training staff on the BEE scorecard; - Ensure implementation of the BEE score card | - BEE Scorecard developed and approved by Council; - Training conducted; - Full implementation of the BEE scorecard. | End of September 2007 | Municipal Manager; CFO |
| 2.5 | Credit control and debt Policy | - Conduct a review of the Credit control and debt policy; - Workshops conducted on the reviewed Credit control and debt policy | - Reviewed Credit control and debt policy approved by Council; - Workshops conducted on the reviewed policy | End of September 2007 | Municipal Manager; CFO |
| 2.6 | Revenue collection strategies & targets for cost recovery | - Conduct an assessment of the current revenue collection rate; - Develop revenue collection strategies; - Identify and outline the targets for cost recovery | - An assessment report on the current collection rate; - Revenue collection strategy developed and approved; - Targets for cost recovery outlined and implemented | End of September 2007 | Municipal Manager; CFO |
| 2.7 | Implementation of valuation rolls | - Finalise the valuation roll process; - Issue notifications to all affected people; - Implement the valuation roll | - All properties valued; - Members of the public informed of the valuation roll; - Valuation roll implemented | End of December 2007 | Municipal Manager; CFO |
| 2.8 | Improvement of billing strategies and systems | - Conduct an audit of the current billing strategies and systems; - Conduct a review of the billing strategies; - Develop an effective billing system | - Audit report on billing strategies and system developed; - A reviewed report on the billing strategies adopted and implemented; - An effective and efficient billing system developed. | End of March 2008 | Municipal Manager; CFO |
| 2.9 | Compliance with accounting standards and systems | - Conduct an assessment on the current situation regarding accounting standards and systems; - Identify gaps in the compliance of the accounting standards and systems; - Ensure that corrective measures are put in place. | - Report on the state of compliance produced; - Gaps in the compliance of the standards and systems outlined; - Corrective measures implemented. | End of December 2007 | Municipal Manager; CFO |
| 3. | Budget and Expenditure Management |  |  |  |  |
| 3.1 | Preparation, and adoption of budget in compliance with MFMA | - Develop a budget process plan; - Ensure that the process plan is approved by Council; - Ensure that the process plan is implemented | - Process plan developed and approved; - Budget process plan implemented. | End of September 2007 | Municipal Manager; CFO |
| 3.2 | Monthly and Quarterly Financial Reports | - Compile monthly and quarterly reports; - Ensure that reports are submitted to Council and relevant stakeholders; - Apply corrective measures on gaps outlined in the reports | - Monthly and quarterly reports compiled; - Report approved by Council | Monthly and quarterly | Municipal Manager; CFO |
| 3.3 | Financial Statements | - Compile the financial statements; - Ensure that the statements are submitted to the Auditor General | - Financial statements compiled and approved; - Financial statements submitted to the Auditor General. | End of August 2007 | Municipal Manager; CFO |
| 3.4 | Implementation Plan to address audit reports of the Auditor General | - Develop an implementation plan to address audit reports of the Auditor General; - Ensure that the implementation plan is adhered to by all staff | - Implementation plan developed; - Adherence to the implementation plan. | End of September 2007 | Municipal Manager; CFO |

KPA 5:  Good Governance and Public Participation

| NO | PLANNED INTERVENTIONS | HIGH LEVEL ACTIVITIES | DELIVERABLES | TIMEFRAME | RESPONSIBILITY |
| --- | --- | --- | --- | --- | --- |
| 1. | Running of municipal council |  |  |  |  |
| 1.1 | Ordinary and special Council sitting | - Schedule of meetings compiled - Convene and advertise ordinary and special Council sittings; - Ensure that the meetings are open for members of the public; - Ensure that reports are prepared and delivered to members as per Rules of Order; - Ensure that all procedures during sittings are fully adhered to as per Rules of Order | - Programme for meetings approved; - Council sittings convened; - Members of the public in attendance during the sittings; - Agenda of the meeting developed and delivered; - Sittings conducted following set procedures. | Quarterly | Municipal Manager; Director/Manager Corporate Service |
| 1.2 | Functionality of Mayoral committee & portfolio committee | - Schedule of meetings developed and approved; - Ensure that agenda items for the committees are compiled and circulated; - Ensure that meetings are convened as per schedule; - Put in place mechanisms to ensure that all members attend committee meetings; - Reports from the committees generated to the Mayoral/ Executive Committee and Council | - Programme approved by members and submitted to Council; - Inputs made on the items for all committees; - Meetings convened per schedule; - Attendance report; - Reports submitted to Council. | Monthly | Municipal Manager; Director/Manager Corporate Service |
| 1.3 | By-Laws, Policies and Strategy approval | - Compile all outstanding By-Laws, policies and strategies; - Conduct a public participation process on the by-laws and relevant policies | - By-laws approved and gazetted; | End of March 2008 | Municipal Manager; Director/Manager Corporate Service |
| 1.4 | Conducting of by-laws in compliance with Municipal Electoral Act 2002 | - Ensure that by-laws are compiled in line with legislative framework. | - Credible by-laws. | On-going | Municipal Manager; Director/Manager Corporate Service |
| 2. | Public Participation, Ward Committees |  |  |  |  |
| 2.1 | Establishment and Functionality of Wards committees | - Ensure that all ward committees are established; - Skills audit on all ward committee members developed; - Ensure that training is conducted on all ward committee members; - A programme of action is developed for ward committee activities; - Ensure that reports are submitted to Council; - Establish ward committee forum in all municipalities and the district. | - Ward committees established; - Skills audit report; - Training programme developed; - Ward committee plan; - Reports compiled; - Ward committee forum established. | End of March 2007; End of May 2007; End of June 2007 End of June 2007 Monthly End of April 2007 | Municipal Manager; Director/Manager Corporate Service |
| 2.2 | Budget and administrative support for ward committee | - Ensure that a needs assessment is conducted on all wards; - Ensure that resources are made available for ward committee members; | - Needs assessment report; - Resources allocated; | End of May 2007 End of May 2007 | Municipal Manager; Director/Manager Corporate Service |
| 2.3 | Ward IDP Plan | - Conduct training on the ward IDP plans; - Develop a process plan for the ward IDP plans; - Ensure that ward IDP plans are submitted to Councils; - Ward IDP plans incorporated into the IDP/Budget/PMS | - Training conducted; - Ward IDP process plan approved; - Ward IDP Plans approved; - Ward IDP plans included in the IDP/Budget/PMS | End July 2007; End of August 2007; End of March 2008; End of May 2008 | Municipal Manager; Planning and Economic Director/Managers; CFO |
| 2.4 | Involvement of CDW | - Ensure that CDW’s attend ward committee meetings; - Ensure that activities of the CDW are shared with the members of the ward committees. | - Attendance of meetings by CDW’s; - Activity reports are presented and discussed. | Monthly | Municipal Manager; Manager in the Office of the Mayors |
| 3. | Corporate Governance |  |  |  |  |
| 3.1 | Implementation of Communication Policies and Strategies |  |  |  |  |
| 3.1.1 | Communication Strategy | - Establish comprehensive framework for communication “within the local circle” ; - Develop a district wide communication strategy | - Communication framework developed and approved; - District wide communication strategy developed and approved | End of June 2007 | Municipal Manager; Communication Unit |
| 3.1.2 | Communication unit | - Ensure establishment of a communication unit; - Ensure that the unit is well resourced. | - Communication unit established and resourced. | End of June 2007 | Municipal Manager; Communication Unit |
| 3.1.3 | Community satisfaction surveys | - Conduct a community satisfaction survey; - Ensure that the findings of the survey are presented to communities and stakeholders; - Findings of the survey be implemented | - Community satisfaction survey report; - Report presented to all stakeholders; - Findings implemented. | End of August 2007 | Municipal Manager; Director/Manager Corporate Service |
| 3.1.4 | Functional complaint management systems | - Conduct an assessment of the current complaint management systems; - Review the current system; - Develop an effective and efficient complaint management system. | - Complaint management system in place; | End of September 2007 | Municipal Manager; Director/Manager Corporate Service |
| 3.2 | Municipal Information Technology | - Conduct an assessment of the current municipal information Technology; - Implement improved measures. | - Analysis report on municipal information technology; - Findings implemented | End of August 2007 | Municipal Manager; Director/Manager Corporate Service |
| 3.2.1 | Municipal Information Masters Systems Plan | - Compile a Municipal Information Systems Plan; | - Municipal Information Systems Plan developed. | End of August 2007 | Municipal Manager; Director/Manager Corporate Service |
| 3.2.2 | Municipal website functional and updated | - Develop and update the municipal website. | - Website developed and updated | Monthly | Municipal Manager; Director/Manager Corporate Service |
| 3.2.3 | Provision of municipal services via electronic communication | - Investigate the mechanisms need to provide municipal services via electronic communication | - Municipal services provided via electronic communication | End of June 2008 | Municipal Manager; Director/Manager Corporate Service |
| 4. | Fraud and Anti Corruption Implementation |  |  |  |  |
| 4.1 | District Fraud Prevention and Anti-Corruption Strategies and mechanism | - Develop a district wide fraud prevention and anti-corruption strategies and mechanisms; - Establish audit committees at district and municipal level (Risk Management). - Establish a shared anti-corruption forum. | - Fraud Prevention and Anti-Corruption Strategies developed; - District wide audit committee established; - Shared anti-corruption forum established. | End June 2007 | Municipal Manager; Director/Manager Corporate Service |